## Sheet1
Routing Checklist
© 2023 Verno Consulting, llc. All rights reserved.
Step # | Action | Description | Assigned To | Start Date | Target Completion Date
Phase 1 - Prep-Work & Set-Up
1 | Determine your reroute goals and strategy | Reduce miles, change # of routes, reduce hours/OT, increase cases / truck, etc.
2 | Verify account information | Address, contact info, days & times unable to accept deliveries, etc.
3 | Develop service times per account per stop | Identify the time required to complete each stop factoring in new service policy, sales model & delivery methodology
Phase 2 - Strategic Development
4 | Develop your sales strategy | Channel vs. geo sales, level of sales reps, pre-sell vs. inside sales, online ordering, etc.
5 | Determine changes in delivery methods | Fleet configuration (sidebay, end loader, non-CDL A trucks, etc.), use of helpers, use of chasers, pallet vs. carts, etc.
6 | Develop length of workday standards | For sales, delivery & merch: total length of work day (8hrs, 9hrs, etc.) and # of days / week worked (4 days, 4.5, 5 days, etc)
7 | Formalize the service policy | How often each account will be scheduled to be serviced (sales, delivery & merch)
8 | Classify accounts | Apply new service policy, sales model, delivery methodology to each accounts
9 | Determine rationale for allowable exceptions prior to scrubbing accounts | Chain? Cash? Space? Draft? Owner owns multiple accounts? Prestige? Seasonal? Other?
10 | Identify accounts that are exceptions to service policy | Exception defined as any account that will receive service other than what the service policy dictates
11 | Finalize all account specific data to hand off to routing | Final frequency, sales model, delivery method, service time, etc.
Phase 3 - Routing
12 | Determine route territories - solve for the best solution
13 | Develop new delivery routes | Always route delivery first: 1) multiple reps feed 1 truck, 2) most expensive function should be optimized
14 | Review preliminary routes with delivery supervisors
15 | Provide new delivery route information to the sales team
16 | Develop new sales routes
17 | Review new sales routes with sales supervisors | Every account that moves service day should be backfilled 1-for-1 to keep new routes balanced
Phase 4 - Implementation Plan
18 | Notify employees of new routes | Allow time for employees to exchange information for accounts moving from route to route
19 | Develop a customer notification strategy & tracking methodology | Account specific notification letters? Word of mouth? Phone Call?; Account signature? RAS survey?
20 | Identify accounts that will experience service change
21 | Supervisors visit accounts that will show strong distain for service changes
22 | Notify remaining accounts | Typically 3-4 weeks to complete depending on # of accounts and degree of change
23 | Modify new routes based on feedback from notification process
24 | Factor impact new routes will have on compensation
25 | Establish measurements to monitor reroute effectiveness
26 | Implement new routes